## Active
Id | Title | Status | Category | Created
23 | what do these lines do? Application.EnableVisualStyles(); Application.SetCompatibleTextRenderingDefault(false); | Todo | Task | 8/9/2018
38 | support applying color while zoomed in or out | Todo | Task | 8/12/2018
33 | undo, redo coloring a section on the image | Todo | Task | 8/11/2018
37 | apply color over color without changing underlying values - change section back to grayscale - then to the new color | Todo | Task | 8/12/2018
42 | bug: expanded palette covers part of picturebox | Todo | Task | 8/15/2018
46 | add "100%" size button | Todo | Task | 8/16/2018
35 | set and check tolerance for "black" and "white" - "blacks" will be left untouched - "whites" will be treated as pure white, which will in effect alter them to white | Todo | Task | 8/12/2018
13 | open edit palette mode - add swatches - remove swatches - change color of swatch - reorder swatches - undo, redo until pane is closed - save changes before leaving pane (save as text file - or, what do other programs use?) (no duplicate colors allowed) | Todo | Task | 8/9/2018
34 | when zooming, if a scroll bar is all the way to min or max, keep it there | Todo | Task | 8/11/2018
21 | when resizing windows, default behavior is to keep the same section of image in the viewing pane - so expanding window would in effect zoom in | Todo | Task | 8/9/2018
24 | remember windows size from last closing - full screen vs not - default not-full-screen size open with this size | Todo | Task | 8/9/2018
27 | include support contact information -wohaste email -paint landing page on website -github page | Todo | Task | 8/9/2018
28 | include donation information -patreon | Todo | Task | 8/9/2018
19 | design an icon apply to windows, desktop icon, and uninstall icon | Todo | Task | 8/9/2018
22 | check through the program Properties >> Assembly Info again, make sure all is accurate | Todo | Task | 8/9/2018
16 | that should be it for minimum viable save as Version 1 | Todo | Task | 8/9/2018
17 | build installer for Version 1 and save it in a separate folder to keep | Todo | Task | 8/9/2018
18 | update website with project, landing page, and links | Todo | Task | 8/9/2018
25 | EVERYTHING BELOW HERE IS VERSION 2 | Todo | Task | 8/9/2018
26 | remember last used directory (save or open) and default to there in file dialogs | Todo | Task | 8/9/2018
43 | on deep zoom, when image is getting too big, switch to zooming on just a segment of the masterImage - this will complicate scrollbars and color placement | Todo | Task | 8/15/2018
29 | how to programs auto-update? | Todo | Task | 8/9/2018
47 | read about faster bitmap operations: https://www.codeproject.com/Tips/240428/Work-with-Bitmaps-Faster-in-Csharp-3 | Todo | Task | 8/21/2018

## Inactive
Id | Title | Status | Category | Created | Done
45 | display closable modal "Please Wait" while coloring image - with "Cancel Color" option that will stop the thread and cancel the changes UPDATED: show status bar message | Done | Task | 8/15/2018 | 8/21/2018
44 | move coloring operations into another thread - queue incoming commands - handle one at a time in another thread, updating display between each one | Done | Task | 8/15/2018 | 8/21/2018
41 | bug: on some colors (oranges esp.) adjusting the saturation gives a too bright color - keep it in the gray range | Done | Task | 8/15/2018 | 8/16/2018
36 | what to rename ColorPalette library to so it does not conflict with object ColorPalette? | Done | Task | 8/12/2018 | 8/16/2018
11 | save changes to image - bitmap - png - jpg | Done | Task | 8/9/2018 | 8/15/2018
40 | zoom in needs to keep pixels clear instead of letting it blur together | Done | Task | 8/13/2018 | 8/15/2018
39 | bug: it isn't actually keeping the grayscale - wow, spent days debugging and it was just a test-line outside the area I was looking at | Done | Task | 8/12/2018 | 8/15/2018
32 | fill in a section of color on the image | Done | Task | 8/11/2018 | 8/12/2018
31 | select a palette color | Done | Task | 8/11/2018 | 8/11/2018
20 | program preference setting: how wide the palette area is - let user drag and drop divider to change palette width - minimum is 3 swatches, max is maybe 12 - save setting and reuse on next progam open (maybe instead of drag-n-drop the border, there are little < > arrow buttons that will expand/contract space one swatch at a time) | Done | Task | 8/9/2018 | 8/11/2018
9 | display a default palette along the side of the window - give it a vertical scroll when needed | Done | Task | 8/9/2018 | 8/11/2018
8 | build 1 to 3 default palettes - downloaded some Photoshop palettes | Done | Task | 8/9/2018 | 8/11/2018
4 | scroll horizontal and vertical when zoomed in | Done | Task | 8/9/2018 | 8/10/2018
3 | zoom in and out of image | Done | Task | 8/9/2018 | 8/9/2018
30 | resize image to fit window as it resizes | Done | Task | 8/9/2018 | 8/9/2018
2 | open an image and display it in a window at default size | Done | Task | 8/9/2018 | 8/9/2018
1 | new window's console app - version 0 until minimum viable is complete | Done | Task | 8/9/2018 | 8/9/2018

## Config
Status | Active | Category | Max Id
Todo | Active | Task | 47
Done | Inactive | Bug