## Active
Id | Title | Status | Category | Created
50 | design test that generates value scale for many different colors, easy to scan with the eye - for instance, sometimes the adjusted color gets darker than the lightest "black", leaving a paler ring around it | Todo | Task | 8/22/2018
34 | when zooming, if a scroll bar is all the way to min or max, keep it there | Todo | Task | 8/11/2018
87 | refactor all history actions and panels to use proper events instead of delegate properties | Todo | Task | 8/25/2018
49 | applying color is pretty fast even on large image but removing the color is really slow | Todo | Task | 8/22/2018
21 | when resizing windows, default behavior is to keep the same section of image in the viewing pane - so expanding window would in effect zoom in | Todo | Task | 8/9/2018
86 | bug: Palette > New > Done get error because no filename to open in main form | Todo | Task | 8/24/2018
54 | make a MasterImage class that one-time figures out all the regions in a background thread and provides that data to the color worker | Todo | Task | 8/23/2018
88 | to be consistent with System.Convert naming standards update ConvertColors - To<Type>(FromType) - <FromType>To<Type>(list of generic params) | Todo | Task | 8/25/2018
90 | name all Settings properties in OneImageForm with prefix "Setting" for consistency | Todo | Task | 8/25/2018
53 | prompt to save if image has changed since last save - on closing program - on opening new image Add this tracking to MasterImage class | Todo | Task | 8/23/2018
51 | replace Rabbit with smaller and better divided image | Todo | Task | 8/22/2018
76 | full documentation of Perpetual Paint | Todo | Task | 8/24/2018
91 | in public projects, make a Release directory to put each Version into | Todo | Task | 8/26/2018
35 | set and check tolerance for "black" and "white" - "blacks" will be left untouched - "whites" will be treated as pure white, which will in effect alter them to white | Todo | Task | 8/12/2018
79 | documentation: include request for sample palette files for the specific formats/color spaces I can't verify because I don't have a test file to load - maybe in the actual error messages from the library, too - like, send me the file you are trying to read so I can add support for it | Todo | Task | 8/24/2018
85 | put in top of documentation that program is being actively developed, so open to bug reports and feature requests | Todo | Task | 8/24/2018
80 | in Paint documenation describe the use-case of converting between palette formats: open file, edit palette, save as new format | Todo | Task | 8/24/2018
77 | full documentation of support library Colors | Todo | Task | 8/24/2018
78 | full documentation of support library GUI | Todo | Task | 8/24/2018
52 | in documentation recommend user keeps an original b/w copy to go back to if conversion errors build up with lots of editing | Todo | Task | 8/22/2018
27 | include support contact information -wohaste email -paint landing page on website -github page | Todo | Task | 8/9/2018
28 | include donation information -patreon | Todo | Task | 8/9/2018
19 | design an icon apply to windows, desktop icon, and uninstall icon | Todo | Task | 8/9/2018
22 | check through the program Properties >> Assembly Info again, make sure all is accurate | Todo | Task | 8/9/2018
16 | that should be it for minimum viable save as Version 1 | Todo | Task | 8/9/2018
17 | build installer for Version 1 and save it in a separate folder to keep | Todo | Task | 8/9/2018
18 | update website with project, landing page, and links | Todo | Task | 8/9/2018
81 | VERSION 1.5: PROJECTS | Todo | Task | 8/24/2018
82 | secondary optional form open multiple files select one to see and edit in main form | Todo | Task | 8/24/2018
83 | save project: - list of images - a palette select a file format to use, save in plain text | Todo | Task | 8/24/2018
84 | open project | Todo | Task | 8/24/2018
25 | EVERYTHING BELOW HERE IS VERSION 2 | Todo | Task | 8/9/2018
57 | create custom trackbar control - drag and drop - small adjustments with arrow keys or buttons - shows selected color larger above pointer put in WithoutHaste.Windows.GUI | Todo | Task | 8/24/2018
65 | edit palette: reorder | Todo | Task | 8/24/2018
58 | possible update to New Color Dialog change Hue selector into quarter-circle curve and nestles around the Saturation/Value selector | Todo | Task | 8/24/2018
61 | New Color Dialog - have Saturation/Value trackbars both start in upper-left at black | Todo | Task | 8/24/2018
26 | remember last used directory (save or open) and default to there in file dialogs | Todo | Task | 8/9/2018
43 | on deep zoom, when image is getting too big, switch to zooming on just a segment of the masterImage - this will complicate scrollbars and color placement | Todo | Task | 8/15/2018
74 | edit palette: possibly replace "add color" button with a default extra swatch at the end of the list with a "plus sign" on it or a "plus" icon in the toolbar | Todo | Task | 8/24/2018
29 | how to programs auto-update? | Todo | Task | 8/9/2018
47 | read about faster bitmap operations: https://www.codeproject.com/Tips/240428/Work-with-Bitmaps-Faster-in-Csharp-3 | Todo | Task | 8/21/2018
60 | look into this website about color formats http://colorizer.org/ | Todo | Task | 8/24/2018

## Inactive
Id | Title | Status | Category | Created | Done
89 | having problems with imprecise color format conversions it's really important they be perfectly reversible | Done | Task | 8/25/2018 | 8/25/2018
59 | refactor WithoutHaste.Drawing.Colors HSV to use ints instead of floats (0-360, 0-100, 0-100) CANCELLED more research online shows that float is proper for HSV | Done | Task | 8/24/2018 | 8/25/2018
69 | new color: enter an hsv value | Done | Task | 8/24/2018 | 8/25/2018
68 | new color: enter a hexadecimal value | Done | Task | 8/24/2018 | 8/25/2018
67 | new color: enter an rgb value | Done | Task | 8/24/2018 | 8/25/2018
71 | edit palette: display rgb/hexdecimal/hsv values of selected color | Done | Task | 8/24/2018 | 8/24/2018
24 | remember windows size from last closing - full screen vs not - default not-full-screen size open with this size | Done | Task | 8/9/2018 | 8/24/2018
75 | remember last open palette and reopen it next time program starts | Done | Task | 8/24/2018 | 8/24/2018
55 | use SwatchPanel object for main palette display | Done | Task | 8/23/2018 | 8/24/2018
56 | change names of dialog-only forms to XDialog | Done | Task | 8/23/2018 | 8/24/2018
72 | entirely new palette | Done | Task | 8/24/2018 | 8/24/2018
66 | edit palette: undo/redo all changes | Done | Task | 8/24/2018 | 8/24/2018
62 | edit palette: save changes see updates in main form - save or lose changes on close | Done | Task | 8/24/2018 | 8/24/2018
70 | edit palette: add new color, but start from existing color | Done | Task | 8/24/2018 | 8/24/2018
64 | edit palette: edit color in place | Done | Task | 8/24/2018 | 8/24/2018
63 | edit palette: remove color | Done | Task | 8/24/2018 | 8/24/2018
13 | open edit palette mode - add swatches | Done | Task | 8/9/2018 | 8/24/2018
42 | bug: expanded palette covers part of picturebox and statuspanel | Done | Task | 8/15/2018 | 8/23/2018
33 | undo, redo coloring a section on the image | Done | Task | 8/11/2018 | 8/23/2018
48 | on error popup: display all nested errors | Done | Task | 8/22/2018 | 8/22/2018
37 | apply color over color without changing underlying values - change section back to grayscale - then to the new color | Done | Task | 8/12/2018 | 8/22/2018
38 | support applying color while zoomed in or out | Done | Task | 8/12/2018 | 8/21/2018
46 | add "100%" size button | Done | Task | 8/16/2018 | 8/21/2018
45 | display closable modal "Please Wait" while coloring image - with "Cancel Color" option that will stop the thread and cancel the changes UPDATED: show status bar message | Done | Task | 8/15/2018 | 8/21/2018
44 | move coloring operations into another thread - queue incoming commands - handle one at a time in another thread, updating display between each one | Done | Task | 8/15/2018 | 8/21/2018
41 | bug: on some colors (oranges esp.) adjusting the saturation gives a too bright color - keep it in the gray range | Done | Task | 8/15/2018 | 8/16/2018
36 | what to rename ColorPalette library to so it does not conflict with object ColorPalette? | Done | Task | 8/12/2018 | 8/16/2018
11 | save changes to image - bitmap - png - jpg | Done | Task | 8/9/2018 | 8/15/2018
40 | zoom in needs to keep pixels clear instead of letting it blur together | Done | Task | 8/13/2018 | 8/15/2018
39 | bug: it isn't actually keeping the grayscale - wow, spent days debugging and it was just a test-line outside the area I was looking at | Done | Task | 8/12/2018 | 8/15/2018
32 | fill in a section of color on the image | Done | Task | 8/11/2018 | 8/12/2018
31 | select a palette color | Done | Task | 8/11/2018 | 8/11/2018
20 | program preference setting: how wide the palette area is - let user drag and drop divider to change palette width - minimum is 3 swatches, max is maybe 12 - save setting and reuse on next progam open (maybe instead of drag-n-drop the border, there are little < > arrow buttons that will expand/contract space one swatch at a time) | Done | Task | 8/9/2018 | 8/11/2018
9 | display a default palette along the side of the window - give it a vertical scroll when needed | Done | Task | 8/9/2018 | 8/11/2018
8 | build 1 to 3 default palettes - downloaded some Photoshop palettes | Done | Task | 8/9/2018 | 8/11/2018
4 | scroll horizontal and vertical when zoomed in | Done | Task | 8/9/2018 | 8/10/2018
3 | zoom in and out of image | Done | Task | 8/9/2018 | 8/9/2018
30 | resize image to fit window as it resizes | Done | Task | 8/9/2018 | 8/9/2018
2 | open an image and display it in a window at default size | Done | Task | 8/9/2018 | 8/9/2018
1 | new window's console app - version 0 until minimum viable is complete | Done | Task | 8/9/2018 | 8/9/2018

## Config
Status | Active | Category | Max Id
Todo | Active | Task | 91
Done | Inactive | Bug